# Statement of Work
 for
 Local

Meridien Conference
Promotion Program

Presented by

April 22, 2017

The following is a statement of work to be performed by GlobalCorp on behalf of Local for the City of Meridien Conference (“conference”).

Local Needs Assessment

Background

Since 1996, Local has provided businesses and organizations what they need to be noticed and successful in and around the beautiful city of Meridien.

Goals

The City of Meridien Conference, produced by Local, is where more than thousands of the area's leaders, influencers, buyers and business decision makers of all levels and backgrounds gather to shape the future of our city and to gain a competitive edge through intensive knowledge sharing and unique networking opportunities.

City of Meridien Conference attendees will discover all that the city has to offer, from it's rich history to its diverse culture to its beautiful natural surroundings.

Local is requesting two phases of event promotion services. The first phase involves two-rounds of calling to past attendees and follow-ups from last year’s promotion efforts. On June 13, 2017, Local will send event registration information to previous conference attendees.

Phase 2 event promotion efforts will begin in August or September of 2017 to its database of contacts. GlobalCorp will employ a model to drive potential attendees to the Local registration landing page where they may then register for the event.

It is understood that the actual number of persons who register will depend upon several factors: the promoted agenda, registration and travel costs, possible conflicting events, and the existing needs of the contacts/companies invited.

Services

Database Best Practices

GlobalCorp stresses the strategic importance database resources bring to marketing efforts. In architecting an effective and efficient event promotion solution for Local, GlobalCorp will incorporate the following best practices into its reporting and system infrastructure: just-in-time reporting and continuous monitoring of analytical data, messaging optimization, interest analysis, referral generation, and record analysis.

Analytics

GlobalCorp will deliver to Local a detailed report showing the distribution of the database by contact type and interests. With this reporting, GlobalCorp will be able to deliver messaging to present the value of the conference based on each prospect’s interests.

Our report will detail:

- the total number of companies in the database, including

  - the total number of contacts per company

  - the number of sites per company

  - the industry/segment of each company

- the total number of contacts in the database

- data on the types of contacts in the database, including

  - personal interest demographics

  - business interest demographics

- data on contacts interest in the conference, including

  - previous attendance

  - interest/non-interest in the conference

  - interest/non-interest in conference session agenda

Messaging Optimization

The City of Meridien Conference means different things to different constituencies. To past attendees, the event is an opportunity to re-connect with peers and colleagues and to strengthen their networks. To new prospects, it’s an opportunity to discover everything that Meridien has to offer.

Our messaging system will enable GlobalCorp to effectively convey the different value propositions of the conference based on who the target audience is. GlobalCorp will work consultatively with Local to identify a messaging model that exceeds Local’s goals for registration and attendance.

Interest Analysis

Analysis of both reasons to register and not register are critically important and our ability to modify messaging based on just-in-time analysis is another factor in exceeding registration goals.

In particular, analysis of “no interest” based on topic is one of the most important issues to monitor. These types of metrics will help us alter the key messages as provided by Local.

Monitoring

Thorough monitoring of invalid data is another critical success factor that requires us to work proactively with Local. Monitoring needs to occur at all levels. If we find a contact that is invalid, due to a company name change or incorrect telephone number, we apply this invalidity to all occurrences tied to that data.

Event Promotion

Upon completion of setup, a program of promotional calling by GlobalCorp specialists will begin. The event will be promoted to each prospect and they will be queried as to whether they received an invitation and whether they plan to attend.

If they plan to attend, all demographic information will be confirmed and an email address will be obtained, where possible. Potential registrants will be referred to the Meridien Conference landing page to register.

Contacts that have been reached and are interested but that are undecided as to whether they will attend, or who did not receive an invitation, will be emailed a copy of the event invitation for reference.

All changes will be entered into the database. Once a prospect has indicated an intention to register that name will be removed from the call list.

As part of this program, GlobalCorp will establish a dedicated toll-free number for prospects to return messages left on behalf of Local. Return calls from prospects are automatically directed to the GlobalCorp’s specialists assigned to the Meridien Conference program for immediate response.

Tactical Support

Local will provide GlobalCorp with general information about the conference for the development of interactive help screens used during outbound and inbound calling.

GlobalCorp’s experienced scriptwriters will work with Local in developing a script. The final script will not be implemented until approved by Local.

Local will provide to GlobalCorp written materials suitable for electronic transmission via email to prospects that request it.

Management and Reporting

Local will provide the name of a contact person with whom all communication should be conducted and to whom all reporting should be forwarded.

GlobalCorp will assign a Project Manager whose responsibilities include internal resource coordination, liaison between GlobalCorp and Local, and overall program accountability.

Pricing and Payment

Pricing

| Description | Quantity | Unit | Rate | Amount |
| --- | --- | --- | --- | --- |
| Outbound Event Promotion | 1500 | Hours | $25 | $37500 |
| Program Management | 135 | Hours | $40 | $5400 |
| Data Management | 100 | Hours | $25 | $2500 |
| Data Reporting | 105 | Hours | $15 | $1575 |
| Electronic Fulfillment | Waived |  |  | $0 |
| Inbound Response Management | 1000 | Call | $2 | $2000 |
| Email Blast | 1 | Blast | $340 | $340 |
| Data Entry and Cleaning | 1 |  | $3600 | $3600 |
| On-site Technician | 2 | Day | $325 | $650 |
| Airfare | 1 |  | $300 | $300 |
| Ground | 2 |  | $50 | $100 |
| Hotel | 3 | Night | $150 | $450 |
| Per Diem | 3 | Day | $75 | $225 |
| Shipping Costs | 20 | Boxes | $40 | $800 |
| Discount |  |  |  | $2000 |
| Estimated Total |  |  |  | $53440 |

Payment Schedule

GlobalCorp will invoice Local for the estimated total, and this invoice is due NET30 days from invoice date.

Terms and Conditions

Assumptions

Assumptions were made in the development of this proposal and are directly related to its associated pricing structure. Any modifications initiated by Local or GlobalCorp to the proposed scope of this work, may result in an amendment to this agreement to include changes in cost and scheduling. All proposed changes would be agreed upon in writing between GlobalCorp and Local prior to implementation.

Termination

Any party to this Agreement may terminate its portion of the Agreement by sending written notice of termination to the others not less than 30 days prior to such termination. Upon said termination, GlobalCorp shall be paid for all work performed through the termination date. The payment will be due NET30 from termination date. All work product completed through the termination date shall be sent to Local along with any database or other materials (written or otherwise) supplied by Local to support the program.

Force Majeure

Neither party shall be liable for any delay or failure in performance due to Force Majeure, which shall mean acts of God, earthquake, labor disputes, changes in law, regulation or government policy, riots, war, fire, terrorist attack, epidemics, acts or omissions of vendors or suppliers, transportation difficulties or other occurrences which are beyond either party’s reasonable control. In the event that GlobalCorp is prevented or delayed in the delivery of the work product for reasons beyond its control, such delivery shall take place as soon thereafter as is reasonably possible. In the event of Force Majeure, Local will be obligated to pay only for services that have been rendered prior to the Force Majeure event.

Approval and Signature

This proposal, when signed by both parties, shall constitute a basic agreement between Local and GlobalCorp, incorporating the understanding between the parties.

Local

Signature

Name

Title

Date

Purchase Order Number

Reference Number

GlobalCorp

Signature

Rye Woodard

Name

President

Title

Date

Tax ID Number

osal.